## Instructions
Purpose
1 | These tools were designed for operational purposes. A description of each tool is below.
Master Facility Fact Sheet
1 | This tool should be used to collect information about a facility—information that would help to inform the planning of how the implementation will be conducted.
2 | Before using this tool, check with the Ministry of Health to see if any other helpful information could be collected that could help in populating facility data in tools such as DHIS 2 or a facility registry.
3 | Use this tool before a facility visit to plan what tools will be needed to collect information during the visit. For example, to collect information about Internet speed, whether a a mobile device or laptop will be needed, etc.
4 | Once completed, share this information with the Ministry of Health so that it can be used in DHIS 2 or a facility registry.
5 | For the team operations lead, use these data to plan the implementation in the Planning Board.
Planning Board
1 | This tool should be used to plan the day-to-day operations of an implementation. It would show the operational lead who will be going to what facility, on which day, with which specific driver, and what distance they will travel.
2 | Use this tool to plan two to three weeks in advance.
3 | Share this plan with team members so they can coordinate their plans.
4 | Once completed, share this information with the Ministry of Health so that it can be used in DHIS 2 or a facility registry.
5 | For the team operations lead, use these data to plan the implementation in the Planning Board.
6 | Be sure to add notes about the facility visit so that if that facility is visited again, the team would know information about the previous visit.

## Master Facility Fact sheet
Province | Districts | Health Facilities | Distance From District Health Office (in Kilometers) | Global Positioning System (GPS) Coordinates: Longitude | Global Positioning System (GPS) Coordinates: Latitude | Type of Facility (Health Center, Health Post) | Urban/Rural | Facility Population | Facility ID | Collect M&E Baseline Data? (Yes or No) | In-Charge Name | In-Charge Contact/Mobile Number | 2nd In-Charge Name | 2nd In-Charge Contact/Mobile Number | Days of the Week That Immunization Services are Provided (e.g., Monday, Wednesday) | Number of Health Workers in Immunization | Does This Facility Have a Maternity Ward? (Yes or No) | Does This Facility Provide Outreach Services? (Yes or No) | How Often Does Community Outreach Take Place? | Primary Power Source | Secondary Power Source | Internet Connectivity (Yes or No) | Current Provider | Internet Speed (Download/Upload) http://www.speedtest.net/ | Recommended Provider Based on Tests | Daytime Security | Evening Security
Southern | Chikankata | Cheeba | 5 |  |  | Health center | Rural health center | 650 | 1001 | No | Dr. Admin Rights | O961123123 | Dr. Knee | O111122233 | Last Tuesday of each month | 2 | No | Yes | Second Tuesday of the month | National grid | Solar | Yes | Airtel | 9.18 Mbps / 8.97 Mbps | MTN | Guard on duty | Guard on duty
Note on D1: Use these data to plan facility visits. Group facilities that are close together for visits on the same day.
Note on E1: Use an application, such as GPS Coordinates, from the Google Play Store.
Note on F1: Use an application, such as GPS Coordinates, from the Google Play Store.
Note on J1: The facility ID should match the ID number provided by the Ministry of Health.
Note on K1: Only use this field if collecting research data.
Note on L1: Use this contact information to notify the in-charge before the next facility visit that the team will arrive.
Note on P1: Use this information to plan for on-site training. This training should happen on the same days as immunization, when possible, to train health workers how to use the tools in the context of the work.
Note on Q1: Use these data to adjust training, where needed. For example, if there are 3 health workers, have 2 team members attend the first training session for support.
Note on R1: This is important for knowing which facilities are collecting birth information data that can be helpful for knowing the denominator for immunizations.
Note on T1: Use these data to plan [please complete the sentence].
Note on U1: The primary power source for facilities could be the national grid or solar power. Please indicate here [please complete sentence].
Note on V1: Facilities may or may not have secondary power sources. For facilities that do not have a secondary power source, conversations about whether or not to provide solar chargers can take place.
Note on W1: Use these data to know which facilities will be able to send data regularly with a digital device, which ones cannot yet do so, and which ones need tools, such as a modem.
Note on X1: This information can be used for planning data bundles.
Note on Y1: If using digital tools such as an electronic immunization register, share these data with software developers so they understand the context of the Internet speed.
Note on Z1: If the Internet speed test in column Y shows that a provider such as MTN may have a faster connection than Airtel, make that recommendation here.
Note on AA1: Use these data to help facilities plan to keep digital tools, such as tablets, safe. This could include locking the tablet away in the in-charge's office during non-immunization days
Note on AB1: Use these data to help facilities plan to keep digital tools, such as tablets, safe. This could include locking the tablet away in the in-charge's office in the evening.

## Planning Board
Hover over the cells in row 2 for guidance in the comments
Day | Date | Benchmarks | District | Facility Name | Urban or Rural | Volume Type (High or Low) | Visit Number | Distance From Office to District Health Office (in Kilometers) | Starting Point | Facility Distance From Starting Point (in Kilometers) | PATH Team Members | Vehicle | Driver Name | Driver Mobile Number | Accommodation Needed? (Yes or No) | Lodge Name if Accommodation Needed (Write N/A if not Applicable) | Notes
Monday | 19/09/2016 | FIRST VISIT Livingstone | Livingstone | Nakatindi | Rural Health Center | High | V1 | 5 | PATH Office | 22 | Paul and Martha | PATH |  |  | No | N/A | Finished
|  |  | Livingstone | Libuyu | Urban Health Center | High | V1 | 6 | PATH Office | 12 | Masaina and Peter | Hired |  |  | No | N/A | Finished
|  |  | Livingstone | Dalice | Urban Health Center | High | V1 | 8 | PATH Office | 6 | Fred and Namupu | Hired |  |  | No | N/A | Facility Closed
|  |  | Livingstone | Airport | Urban Health Center | low | V1 | 3 | PATH Office | 5 | Mandy and Reuben | Hired |  |  | No | N/A | Finished
Tuesday | 20/09/2017 | Visit 1 Livingstone | Livingstone | Dambwa North | Urban Health Center | High | V1 | 12 | PATH Office | 5 | Paul and Martha | PATH |  |  | No | N/A
|  |  | Livingstone | MahatmaGhandi | Urban Health Center | High | V1 | 10 | PATH Office | 8 | Masaina and Peter | Hired |  |  | No | N/A
|  |  | Livingstone | Boma | Urban Health Center | High | V1 | 10 | PATH Office | 4 | Fred and Namupu | Hired |  |  | No | N/A
|  |  | Livingstone | Hicrest | Urban Health Center | High | V1 | 11 | PATH Office | 3 | Mandy and Reuben | Hired |  |  | No | N/A
Wednesday | 21/09/2018 | Visit 1 Livingstone | Livingstone | Nsongwe | Rural Health Center | low | V1 | 15 | PATH Office | 27 | Paul and Martha | PATH |  |  | No | N/A
|  |  | Livingstone | Victoria falls | Rural Health Center | low | V1 | 18 | PATH Office | 13 | Masaina and Peter | Hired |  |  | No | N/A
|  |  | Livingstone | Mosiotunya | Urban Health Center | low | V1 | 17 | PATH Office | 5 | Fred and Namupu | Hired |  |  | No | N/A
|  |  | Livingstone | Mahuluhulu | Rural Health Center | low | V1 | 20 | PATH Office | 35 | Mandy and Reuben | Hired |  |  | No | N/A
Thursday | 22/09/2019 | Visit 1 Livingstone | Livingstone | Maramba | Urban Health Center | High | V1 | 25 | PATH Office | 5 | Paul and Martha | PATH |  |  | No | N/A
|  |  | Livingstone | kasiya | Rural Health Center | low | V1 | 28 | PATH Office | 30 | Masaina and Peter | PATH |  |  | No | N/A
|  |  | Livingstone | Police | Rural Health Center | High | V1 | 29 | PATH Office | 4 | Fred and Namupu | Hired |  |  | No | N/A
|  |  | Livingstone | Prison | Urban Health Center | low | V1 | 24 | PATH Office | 4.5 | Mandy and Reuben | Hired |  |  | No | N/A
Friday | 23/09/2020 | Visit 1 Livingstone | Livingstone | Linda | Urban Health Center | High | V1 | 30 | PATH Office | 6 | Paul and Martha | PATH |  |  | No | N/A
|  |  | Livingstone | Namatama | Urban Health Center | High | V1 | 35 | PATH Office | 4 | Masaina and Peter | PATH |  |  | No | N/A
|  |  | Livingstone | St. Joseph | Urban Health Center | High | V1 | 33 | PATH Office | 3 | Fred and Namupu | Hired |  |  | No | N/A
|  |  | Livingstone | ZAF Clinic | Urban Health Center | low | V1 | 34 | PATH Office | 5 | Mandy and Reuben | Hired |  |  | No | N/A
Saturday
Sunday
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday
Sunday
Note on E2: Use green to show that a facility visit is complete; use red if the visit is not complete.
Note on F2: Use these data to plan for appropriate transport. For example, rural facilities may need an all-wheel-drive vehicle.
Note on G2: Facilities that see more than 50 children each month is considered high volume. Facilities that see 49 or fewer kids per month is considered low volume.
Note on P2: For facilities that are far away, indicate here if the team will need accommodation.
Note on J136: Njobvu, Fred: Staff to be accommodated either in Choma or Monze
Note on J192: Njobvu, Fred: No Lodges in Gwembe district. Accommodation offered either in Monze or Siavonga depending on proximity to facilities
Note on E231: Njobvu, Fred: I need to follow up St. Josephs Mission hospital
Note on E292: Njobvu, Fred: Not appearing on the map. Geographical direction to be ascertained
Note on E305: Njobvu, Fred: Facilities not on the map.